## Manual Chart
資管系所 - 導覽網站 |  |  |  | Github for Group11
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| 討論專題題目 | 2022-10-03 | 2022-10-10 | 7 | All | 100% | bar: WEEK 1 M to WEEK 2 Th
| 尋找資料 | 2022-10-03 | 2022-10-10 | 7 | All | 100% | bar: WEEK 1 M to WEEK 2 Th
| 任務分配 | 2022-10-03 | 2022-10-10 | 7 | All | 100% | bar: WEEK 1 M to WEEK 2 Th
| 網站規劃 | 2022-10-11 | 2022-10-17 | 6 | 林育賢 | 50% | bar: WEEK 2 M to WEEK 2 Th
Second Sample Project
| 網頁設計 | 2022-10-18 | 2022-11-07 | 19 | 杜佳原 | 0% | bar: WEEK 2 M to WEEK 2 Th
| 網站建置 | 2022-10-18 | 2022-11-07 | 19 | 江浩賢 | 0% | bar: WEEK 2 M to WEEK 2 Th
| 網站功能版面設計 | 2022-10-18 | 2022-11-07 | 19 | 林育賢 | 0% | bar: WEEK 2 M to WEEK 2 Th
Third Sample Project
| 網站架構流程檢視 | 2022-11-08 | 2022-11-25 | 17 | 謝秉諭 | 0% | bar: WEEK 2 M to WEEK 2 Th
| RWD網頁檢視、跨裝置測試 | 2022-11-26 | 2022-12-10 | 14 | 杜佳原 | 0% | bar: WEEK 2 M to WEEK 2 Th
| 網頁內容上稿、測試、確認 | 2022-12-11 | 2022-12-18 | 7 | 江浩賢 | 0% | bar: WEEK 2 M to WEEK 2 Th
Fourth Sample Project
| 上線與驗收 | 2022-12-19 | 2022-12-23 | 4 | All | 0% | bar: WEEK 2 M to WEEK 2 Th